**Treatment Courts**

|  |
| --- |
| Treatment #4: Support treatment court programs. |

|  |
| --- |
| **ACTION ITEMS AND OBJECTIVES** |
| 1. **Perform a gap analysis toward a recommendation for the potential expansion of Mental Health Courts**
 |
| Expand Mental Health Courts into unserved areas (new courts) |
| Expand capacity of existing Mental Health Courts |
| 1. **Adequately fund treatment courts**
 |
| 1. **Explore options for participation in a treatment court without having to move to the location of the treatment court.**
 |
| Explore using virtual technology |
| Leverage supervision resources in neighboring counties |
| Explore options for funding opportunities for home visits and transportation |
| 1. **Streamline process of entering treatment court to reach the targeted 50 days from arrest/PV to entrance into a treatment court**
 |
| Gap analysis to determine the current timeline vs. targeted 50 days |
| 1. **Evaluate the ability to more effectively coordinate through programming and processes the transition from a rider to the community in a treatment court model**
 |

|  |
| --- |
| **ACTION ITEM #1** |
| **Perform a gap analysis towards a recommendation for the potential expansion of mental health courts.** |
| **FULL DESCRIPTION** |
| Perform a gap analysis towards a recommendation for the potential expansion of mental health courts.* Expand mental health courts into unserved areas (new courts)
* Expand capacity of existing mental health courts
 |
| **TARGET OBJECTIVES** |
| **1.** | Expand mental health courts into unserved areas (new courts) |
| **2.** | Expand capacity of existing mental health courts. |

|  |
| --- |
| **SMART GOALS TO ACCOMPLISH ACTION ITEM #1 OBJECTIVES** |
| **OBJECTIVE** | **SPECIFIC OUTCOME** | **METRIC FOR ACCOMPLISHMENT** | **TARGET DATE FOR COMPLETION** | **RESPONSIBLE PARTY** |
|  |  |  |  |  |
|  |  |  |  |  |

|  |
| --- |
| **TEAM LEAD** |
| Sharlene Davis | Administrative Office of Courts |
| **OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #1** |
| Scott Ronan | Administrative Office of Courts |
| Cory Barrier | Idaho Department of Correction, Probation and Parole |
| Sandra Barrios | 4th Judicial District |
| **CONSULTING STAKEHOLDERS FOR ACTION ITEM #1** |
| Data and Evaluation Team at ISC |
| **RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #1** |
|  |

|  |
| --- |
| **ACTION ITEM #2** |
| **Adequately fund treatment courts** |
| **FULL DESCRIPTION** |
|  |
| **TARGET OBJECTIVES** |
| **1.** | Conduct a statewide analysis of existing gaps in resources for Treatment Courts to better understand the need for resources and what is working well. |
| **2.** | Identify gaps in funding, resources, and unmet needs throughout the State |
| **3.** | Research how other States are adequately funding Treatment Courts  |
| **4.** | Develop recommendations and identify strategies to adequately fund treatment courts |

|  |
| --- |
| **SMART GOALS TO ACCOMPLISH ACTION ITEM #2 OBJECTIVES** |
| **OBJECTIVE** | **SPECIFIC OUTCOME** | **METRIC FOR ACCOMPLISHMENT** | **TARGET DATE FOR COMPLETION** | **RESPONSIBLE PARTY** |
|  |  |  |  |  |

|  |
| --- |
| **TEAM LEAD** |
| Aimee Austin | 7th Judicial District Treatment Court |
| **OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #2** |
| Muffy Davis | Blaine County Commissioner |
| Ashley Bringhurst | 6th Judicial District Treatment Court |
| Jason Dye | 6th Judicial District |
| Ryan Porter | Administrative Office of Courts |
| **CONSULTING STAKEHOLDERS FOR ACTION ITEM #2** |
|  |
| **RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #2** |
|  |

|  |
| --- |
| **ACTION ITEM #3** |
| **Explore options for participation in a treatment court without having to move to the location for the treatment court** |
| **FULL DESCRIPTION** |
| Explore options for participation in a treatment court without having to move to the location for the treatment court. This may include leveraging virtual technology and supervision resources in neighboring jurisdictions. Explore options for funding opportunities for home visits and for transportation |
| **TARGET OBJECTIVES** |
| **1.** | Explore and consider ways in which individuals may be able to participate in a specialty court with residing within the county. |
| **2.** | Consider the pros and cons of out-of-county participation for specialty courts, including obstacles in funding, home visits, whether a program can remain effective with an out of county residence, etc. |
| **3.** | Is there a sustainable specialty court model that incorporates the use of virtual technology for some, without compromising the integrity and effectiveness of the specialty court |

|  |
| --- |
| **SMART GOALS TO ACCOMPLISH ACTION ITEM #3 OBJECTIVES** |
| **OBJECTIVE** | **SPECIFIC OUTCOME** | **METRIC FOR ACCOMPLISHMENT** | **TARGET DATE FOR COMPLETION** | **RESPONSIBLE PARTY** |
|  |  |  |  |  |

|  |
| --- |
| **ACTION ITEM #3 TEAM LEAD** |
| Judge Tristan Poorman | 1st Judicial District Magistrate |
| **OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #3** |
| Judge Faren Eddins | 7th Judicial District Magistrate |
| Sharlene Davis | Administrative Office of Courts |
| Buddy Winters | Veteran’s Treatment Court |
| **CONSULTING STAKEHOLDERS FOR ACTION ITEM #3** |
|  |
| **RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #3** |
|  |

|  |
| --- |
| **ACTION ITEM #4** |
| **Streamline process of entering treatment court to reach the targeted 50 days from arrest/PV to entrance into treatment court** |
| **FULL DESCRIPTION** |
| Streamline process of entering treatment court to reach the targeted 50 days from arrest/PV to entrance into treatment court to engage participants more efficiently. Gap analysis needs to be done to determine how long it currently takes vs. the targeted 50 days. |
| **TARGET OBJECTIVES** |
| **1.** | Perform gap analysis to determine baseline data. |

|  |
| --- |
| **SMART GOALS TO ACCOMPLISH ACTION ITEM #4 OBJECTIVES** |
| **OBJECTIVE** | **SPECIFIC OUTCOME** | **METRIC FOR ACCOMPLISHMENT** | **TARGET COMPLETION DATE** | **RESPONSIBLE PARTY** |
|  |  |  |  |  |

|  |
| --- |
| **ACTION ITEM #4 TEAM LEAD** |
| Chris Paulson |  |
| **OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #4** |
| Darci Dickinson | Administrative Office of Courts |
| Norm Embry | Latah County Treatment Courts |
| Israel Enriquez | 5th Judicial District Treatment Courts |
| Deputy Patrick Keber | Ada County Sheriff’s Office |
| Kyle Brown | The Center for Hope |
| **CONSULTING STAKEHOLDERS FOR ACTION ITEM #4** |
|  |
| **RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #4** |
|  |

|  |
| --- |
| ACTION ITEM #5 |
| **Evaluate the ability to more effectively coordinate through programming and processes the transition from a rider to the community in a treatment court model.** |
| **FULL DESCRIPTION** |
| Evaluate the ability to more effectively coordinate through programming and processes the transition from a rider to the community in a treatment court model. \* This one will be worked on after action item #4 is completed.  |
| **TARGET OBJECTIVES** |
| **1.** |  |
| **2.** |  |

|  |
| --- |
| **SMART GOALS TO ACCOMPLISH ACTION ITEM #5 OBJECTIVES** |
| **OBJECTIVE** | **SPECIFIC OUTCOME** | **METRIC FOR ACCOMPLISHMENT** | **TARGET COMPLETION DATE** | **RESPONSIBLE PARTY** |
|  |  |  |  |  |
|  |  |  |  |  |

|  |
| --- |
| **ACTION ITEM #5 TEAM LEAD** |
| Judge Michael Tribe | Court of Appeals |
| **OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #5** |
| Israel Enriquez | 5th Judicial District Treatment Courts |
| Deputy Keber | Ada County Sheriff’s Office |
| **CONSULTING STAKEHOLDERS FOR ACTION ITEM #5** |
|  |
| **RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #5** |
|  |