Program Awareness and Reduction of Stigma – Updated 10/28/2025

Promotion #1: Develop an outreach and marketing strategy to increase awareness of publicly and privately funded programs and services. Address and reduce behavioral health stigma.

ACTION ITEMS AND OBJECTIVES

- Integrate 211 and findhelpidaho.org as the central database of services available, facilitating a no wrong door approach.

Partnership between DHW and United Way to ensure resource databases for 211 and findhelp are up to date and accessible by the general public regardless of how they are accessed.

Ensure callers to 211 are connected to appropriate resources on every call and are made aware of online resources available through findhelp as appropriate.

Utilize existing systems in findhelpidaho to serve individuals searching for resources outside of normal business hours/operation hours for 211.

- Promote and provide behavioral health resources to schools, educators, and parents (education programs, professional development, and parental resources).

Promote and implement Sources of Strength program in Idaho Middle and High Schools.

Catalog and promote behavioral health resources, including professional development courses, to teachers and education professionals.

Catalog and promote behavioral health resources to parents.

- Recommend educational programs tailored for rural Idahoans to reduce stigma, increase awareness, and improve understanding of mental health.

Multi-Channel Outreach – Targeted media approach and outreach - statewide

Storytelling & Lived Experience Integration – Develop a path to normalized conversations and peer to peer programs

Skills-Based Training – Develop a plan to implement mental health training and workshops in each Public Health District

Service Awareness & Navigation (Find Help Idaho, 211, Jannus) – Public awareness of mental health resource access / availability and referral pathways

| ACTION ITEM #1 |  |
| --- | --- |
| Integrate 211 and findhelpidaho.org as the central database of services available, facilitating a no wrong door approach |  |
| FULL DESCRIPTION |  |
| Integrate 211 Idaho Careline database with findhelpidaho.org. These two databases serve similar purposes with similar goals but are currently operating independently. Both systems have unique benefits for Idahoans, that, if coupled, could create a more robust, and more comprehensive system for Idahoans to connect to the help and support they need, when they need it. The Idaho Department of Health and Welfare, Division of Family and Community Partnerships, is committed to partnering with United Way Treasure Valley to move the 211 Idaho Careline toward a partnership with findhelpidaho. |  |
| TARGET OBJECTIVES |  |
| 1. | Partnership between DHW and United Way to ensure resource databases for 211 and findhelp are up to date and accessible by the general public regardless of how they are accessed. |
| 2. | Ensure callers to 211 are connected to appropriate resources on every call and are made aware of online resources available through findhelp as appropriate. |
| 3. | Utilize existing systems in findhelpidaho to serve individuals searching for resources outside of normal business hours/operation hours for 211. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #1 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Establish a cross-organizational integration plan | Written plan agreed to by both agencies | 5/31/2025 |  |
| 1. | Assess technical compatibility and integration needs | Systems assessment | 6/30/2025 |  |
| 2. | Develop a unified data management strategy | MOU | 8/3/2025 |  |
| 2. | Pilot the integrated system with key stakeholders | Feedback from testers/users | 12/31/2025 |  |
| 3. | *Fully implement and publicize the integrated system | Public access to joint resources/systems | 2/28/2026 |  |

*Will coordinate with Action Team #4 for outreach

| TEAM LEAD |  |
| --- | --- |
| Laura Denner | Idaho Department of Health and Welfare, Division of Family and Community Partnerships |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #1 |  |
| Casie Jones | Idaho Department of Health and Welfare, Division of Family and Community Partnerships |
| Jen Haddad | Idaho Department of Health and Welfare, Division of Family and Community Partnerships |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #1 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #1 |  |

| ACTION ITEM #2 |  |
| --- | --- |
| Promote and provide behavioral health resources to schools, educators, and parents (education programs, professional development, and parental resources). |  |
| FULL DESCRIPTION |  |
| This action item supports the recommendation to improve student mental health and resilience through evidence-based, peer-led initiatives. The Sources of Strength program is a nationally recognized prevention program that harnesses the power of peer social networks to promote connection, resilience, and help-seeking behaviors. Implementing this program in Idaho schools aims to reduce youth suicide, strengthen protective factors, and build supportive school communities. The overall goal is to normalize mental health conversations and empower students to be agents of positive change in their schools. SOS is currently being used in several schools throughout the state and these schools can be a valuable resource to other schools in their region. https://sourcesofstrength.org/ If we want to reduce the stigma surrounding mental health, especially with children, we must enlist the help of the adults that support them. To that end, we will locate and promote resources, including professional development courses, for teachers, other education professionals, and also provide resources to parents. These resources will provide training on ACEs, PCEs, trauma-informed classrooms, signs to look for students struggling with mental health, and how to seek help for students. We want to promote them heavily so teachers, educators, and parents are aware and proactively create opportunities for them to do so. Promotion of these courses can happen via social media, newsletters, and organizations. |  |
| TARGET OBJECTIVES |  |
| 1. | Promote and implement Sources of Strength program in Idaho Middle and High Schools. |
| 2. | Catalog and promote behavioral health resources, including professional development courses, to teachers and education professionals. |
| 3. | Catalog and promote behavioral health resources to parents. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #2 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Find out the current process and potential barriers to schools adopting Sources of Strength | Cheryl will connect Jackie with Chenele. Chenele will meet with Jackie Yarbrough and SDE staff about the current process for schools to adopt Sources of Strength | 9-30-25 | Chenele Dixon |
| 1. | Address barriers for schools to adopt SoS |  | 9/30/2025 |  |
| 1. | Make a plan for increasing the number of students adopting SoS | Identification of “pilot” schools. Have at least one interested school in each region | 11/30/2025 |  |
| 2. | IEA – Chenele reach out to IEA. | Identify one or more educational contacts to provide insight on needed resources and appropriate locations to house resources | 10/31/2025 |  |
| 3. | Chenele will reach out to Alexis Morgan formerly of state PTA | Find a parent representative(s) to provide insight on resources needed by parents and recommendations on where to house resources. | 10/31/2026 |  |
| 3. | Reach out to assessment centers for recommendations on resource availability | Identify best place for housing parent resources | 10/31/2025 | Cheryl Foster |
| 2. | Compile existing resources for educators |  | 5/31/2026 |  |
| 3. | Compile existing resources for parents |  | 5/31/2026 |  |
| 2. | Determine best location for resources | Publish resources for educators | 7/31/2027 |  |
|  | Determine best location for resources | Publish resources for parents | 7/31/2027 |  |
| 2., 3. | Create a promotion toolkit to distribute to community partners and other organizations to help with promotion. | Double the number of schools participating | 7/31/2027 |  |
| 2.,3. | Measure success. | Metrics on accessing the resources | Yearly after implementation |  |

| TEAM LEAD |  |
| --- | --- |
| Chenele Dixon | Idaho Solutions |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #2 |  |
| Kari Wardle | Idaho Public Television |
| Holly Cunningham | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Quinn Perry | Idaho School Boards Association |
| Andy Grover | Idaho Association of School Administrators |
| Chris Perri | Idaho Education Association |
| Nancy Jones | Twin Falls High School |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #2 |  |
| Same as key implementation staff University of Idaho Project Echo Idaho Department of Education-to help with promotion |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #2 |  |
| Resources: https://sourcesofstrength.org/ Twin Falls High School Sources of Strength Wheel Risks: Sustainable funding for implementation and continuation |  |

| ACTION ITEM #3 |  |
| --- | --- |
| Recommend educational programs tailored for rural Idahoans to reduce stigma, increase awareness, and improve understanding of mental health. |  |
| FULL DESCRIPTION |  |
| The action item directly contributes to the IBHC Strategic Action Plan by reinforcing Program Awareness and Reduction of Stigma, which is the focus of this implementation team. Here's how: 1. Reducing Stigma & Creating Normalcy – By recommending evidence-based programs, this action item helps shift perceptions of behavioral health, positioning it on equal footing with physical health. Education fosters understanding, dispels myths, and encourages open conversations, creating a culture where seeking behavioral health services is normalized. 2. Increasing Awareness & Access – Many Idahoans struggle to find or navigate behavioral health services. Educational programs can bridge this gap by ensuring different populations (e.g., youth, rural communities, workplaces, faith groups) understand what services exist, how to access them, and why they matter. This supports the “no wrong door” approach by making information about available services widely accessible. 3. Reaching People Where They Live, Learn, Work, Play, Worship, and Age – The strategic plan emphasizes supporting behavioral health in all environments. Tailored educational initiatives allow for customized messaging that resonates with diverse communities, ensuring outreach is effective and meaningful. Overall Goal of the Action Item The goal is to increase behavioral health literacy and normalize seeking support for rural Idahoans by ensuring that communities across Idaho have access to accurate, relevant, and engaging education. Through targeted programs, this initiative will: - Address misconceptions and fears around mental health and addiction. - Empower individuals and families to recognize when help is needed and how to access it. - Build resilience by providing tools and knowledge to manage mental well-being. - Strengthen Idaho’s behavioral health infrastructure by fostering community engagement and acceptance. |  |
| TARGET OBJECTIVES |  |
| 1. | Support the 9-8-8 awareness campaign and leverage outreach for behavioral health program awareness |
| 2. | *Increase public awareness of mental health education and resource access / availability and referral pathways |
| 3. | Skills-Based Training – Develop a plan to implement mental health training and workshops in each Public Health District |

*Will coordinate with Action Item #1

| SMART GOALS TO ACCOMPLISH ACTION ITEM #4 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET COMPLETION DATE | RESPONSIBLE PARTY |
| 1. | Catalog available campaign and messaging assets for RBHBs and others to use for local anti-stigma campaigns | Publish list of assets on an accessible website in a spreadsheet | 09/30/2025 | Cheryl Foster |
| 1. | Support the 9-8-8 statewide media campaign using both digital and traditional platforms to disseminate mental health education materials. Use a targeted media approach and outreach- statewide - Digital & Social Media Campaigns – Leverage social media, websites, and online forums to distribute educational materials, videos, and personal stories. - Traditional Media & Public Messaging – Utilize radio, billboards, newspapers, and local TV to reach those without digital access. | Develop Idaho-specific 9-8-8 media and community partner toolkit. Include available assets. | On hold until campaign starts |  |
| 1. | Ensure key campaign assets are available in Spanish | Radio ads in Spanish |  |  |
| 1. | Beef up 9-8-8 landing page with links to community resources Recommend Peer-to-Peer programs (NAMI Idaho; Empower Idaho by Jannus – Peer Support Series; VA) | Easy to navigate list of community resources Ensure resources are also on FindHelp *Request to provide lethal means safety resources on 988 landing page *Link to The Youth Line, a free peer-to-peer help line staffed from 5-11 p.m. by specially trained youth and trained adults at all other times, theyouthline.org |  |  |
| 1. | Reach out to community partners to promote 9-8-8 awareness campaign - Community Partnerships – NAMI Idaho; School Districts; Idaho College Health Coalition; PHDs, Regional Behavioral Health Boards; Magellan; Crisis Care Continuum; Law Enforcement; Tribes | Recruit community partners from each region of the state participate in the 9-8-8 campaign Provide instructions for promoting 9-8-8 and lining to landing page Ask for assistance from community health workers |  |  |
| 1. | 9-8-8 Law Enforcement and First Responder Outreach | Wallet cards for first responders to provide to the public. Targeted information to first responders on their accessibility to 9-8-8 |  |  |
| 1. | Proactively reach out to local television media with 9-8-8 information and human-interest stories Storytelling & Lived Experience Integration (IDHW, Dustin Lapray, Public Involvement Officer can help with interviews/storytelling, use of video equipment) - Feature personal testimonies from individuals who have successfully navigated mental health challenges Normalize conversations around behavioral health through storytelling campaigns | Find local 9-8-8 crisis workers, first responders, and individuals with lived experience to create stories, preferably with a rural focus |  | Wendy Young? |
| 1. | Proactively reach out to print media to provide in-depth stories on 9-8-8 Storytelling & Lived Experience Integration (IDHW, Dustin Lapray, Public Involvement Officer can help with interviews/storytelling, use of video equipment) - Feature personal testimonies from individuals who have successfully navigated mental health challenges Normalize conversations around behavioral health through storytelling campaigns | *Betsy has contacts who may be willing to speak about each of their stories with suicide, two being loss survivors of medical professionals who died from suicide and one a child with her mother who went through a traumatic suicide attempt and hospitalization. |  |  |
| 1. | Develop 9-8-8 campaign outreach strategy for rural Hispanic population | Targeted Spanish radio ads and stories Flyers and printed materials for churches and other community centers |  |  |
| 1. | Contact school counselors and other key community leaders about 9-8-8 | *These efforts are already being implemented in many districts in Idaho through the state’s Suicide Prevention subgrants to public health districts. Our Suicide Prevention Program can collaborate to collect data demonstrating efforts. *These efforts could be further amplified through the Suicide Prevention subgrant to the State Dept. of Education. |  | Dustin |
| 1. | Promote Magellan Crisis Summit and schedule local follow-up workshops and town halls Events & Workshops – Organize town halls, panel discussions, and interactive workshops to provide education in a relatable, engaging way. | Magellan Healthcare Statewide Crisis Summit Invitation Flyer *Identify funds to host showings of The Paradise Paradox. It’s a long overdue film that looks at the mental health crisis that’s been sweeping our mountain towns, https://www.youtube.com/watch?v=rfKvJScZJDg. It would be particularly appropriate in the Wood River Valley, Teton Valley, McCall area, and Silver Valley. I could make connections to try to secure funding in the various communities. Likewise, My Ascension, focused to a youth audience has been very well received in Idaho in a few communities who have hosted the film, https://www.myascension.us. |  |  |
| 2. | Behavioral Health Education and Resource Awareness - Promote Empower Idaho’s lists of behavioral health resources Determine the criteria to be included in the education programs, resources and calendar. Ask for process to add programs. | Ensure that every educational initiative includes clear information on how to access both public and private behavioral health services in Idaho and promote a “no wrong door” approach by recommending easily accessible resource guides and referral pathways. | 10/1/2025 |  |
| 2. | Connect PHDs and community organizations to Empower Idaho for posting resources | PHDs, DHW and grantees list programs on Empower Idaho |  |  |
| 2. | Raise awareness of telehealth locations | Ask IBHA to recruit their providers and payer networks to register with the NRTRC website *Demonstrate the telehealth pod Locator map found at https://findtelehealth.nrtrc.org/map with all Mental Health First Aid courses to make it known that there is access to services even in rural communities. | 12/1/2025 | Liz |
| 2. | Raise awareness of telehealth options | Ask Magellan to promote telehealth and NRTRC website | 12/1/2025 | Brennan |
| 2. | Link NRTRC telehealth location website to Empower Idaho Resources and FindHelp.org |  |  |  |
| 2. | Raise awareness of third spaces | Collect list of public third spaces to post on Empower Idaho and FindHelp.org |  |  |
| 3. | Provide Mental Health First Aid (MHFA) and Crisis Intervention Training (CIT) for key community members, including teachers, employers, and first responders. | Deliver at least one MHFA or CIT session in each of Idaho’s 7 public health districts – focusing on rural counties. *Many of the public health districts are providing or helping to facilitate Mental Health First Aid through the state’s Suicide Prevention subgrant. Our Suicide Prevention Program can collaborate to collect data demonstrating efforts. | 10/1/2026 | Alejandra – Empower Idaho by Jannus |
| 3. | Provide MHFA Facilitator Training for those in rural areas National Council has list of facilitators where we can evaluate areas where there is a dearth of facilitators. | Identify areas to recruit new MHFA facilitators Determine optimal number of facilitators *To locate a list of MHFA trainers in Idaho, please visit https://healthandwelfare.idaho.gov/services-programs/behavioral-health/other-resources under Suicide Prevention Trainings. | 10/31/2025 | Liz |
| 3. | Promote QPR training Contact churches, schools, civil organizations to offer training. | Increase the number of individuals receiving QPR training. Host QPR trainings in rural areas *The Suicide Prevention subgrant already encourages these trainings and collects data. Data can be shared. |  |  |
| 3. | Offer workshops on stress management, resilience-building, and navigating behavioral health services. | Offer at least 1 resilience-building and stress management workshop in each public health district focused on rural populations. | 10/1/2026 |  |

| ACTION ITEM #4 TEAM LEAD |  |
| --- | --- |
| Morgan Van Ry | NAMI Idaho |
| Stewart Wilder | Idaho Behavioral Health Council |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #4 |  |
| Alejandra Del Toro | Empower Idaho |
| Dustin Lapray | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Brennan Serrano | Magellan of Idaho |
| Liz Caval-Williams | Idaho Behavioral Health Association |
| Doug Steel | Lewis-Clark State College |
| Abigail Hacket | Clarvida Crisis Center |
| Rosie Andueza | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Hayden Falkner | Idaho Department of Health and Welfare, Division of Public Health |
| Betsy Hammar | Idaho Department of Health and Welfare, Division of Public Health |
| Tyrin Stevenson | Idaho Department of Health and Welfare, Division of Public Health |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #4 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #4 |  |