Treatment Courts

Treatment #4: Support treatment court programs.

ACTION ITEMS AND OBJECTIVES

- Perform a gap analysis toward a recommendation for the potential expansion of Mental Health Courts

Expand Mental Health Courts into unserved areas (new courts)

Expand capacity of existing Mental Health Courts

- Adequately fund treatment courts

- Explore options for participation in a treatment court without having to move to the location of the treatment court.

Explore using virtual technology

Leverage supervision resources in neighboring counties

Explore options for funding opportunities for home visits and transportation

- Streamline process of entering treatment court to reach the targeted 50 days from arrest/PV to entrance into a treatment court

Gap analysis to determine the current timeline vs. targeted 50 days

- Evaluate the ability to more effectively coordinate through programming and processes the transition from a rider to the community in a treatment court model

| ACTION ITEM #1 |  |
| --- | --- |
| Perform a gap analysis towards a recommendation for the potential expansion of mental health courts. |  |
| FULL DESCRIPTION |  |
| Perform a gap analysis towards a recommendation for the potential expansion of mental health courts. - Expand mental health courts into unserved areas (new courts) - Expand capacity of existing mental health courts |  |
| TARGET OBJECTIVES |  |
| 1. | Expand mental health courts into unserved areas (new courts) |
| 2. | Expand capacity of existing mental health courts. |
| 3. | Determine judicial workload capacity for mental health courts by county |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #1 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1.,2. | Identify data from ISC for gap analysis | D&E will have data points identified that can be pulled from the system | 9/11/2025 | ISC D&E |
| 1.,2. | Identify data needed from DHW | D&E will report on what data they do not have from ISC and will need from DHW | 9/11/2025 | ISC D&E |
| 1.,2. | Identify data needed from IDOC | D&E will report on what data they do not have from ISC and will need from IDOC | 9/11/2025 | ISC D&E |
| 3. | Identify number of eligible individuals by court |  |  |  |
| 2. | Calculate the potential demand for mental health courts by county |  |  |  |
| 1. | Identify counties without mental health courts and number of eligible individuals by county |  |  |  |

| TEAM LEAD |  |
| --- | --- |
| Sharlene Davis | Administrative Office of Courts |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #1 |  |
| Scott Ronan | Administrative Office of Courts |
| Cory Barrier | Idaho Department of Correction, Probation and Parole |
| Sandra Barrios | 4th Judicial District |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #1 |  |
| Data and Evaluation Team at ISC |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #1 |  |
| Funding |  |

| ACTION ITEM #2 |  |
| --- | --- |
| Adequately fund treatment courts |  |
| FULL DESCRIPTION |  |
| Adequately fund treatment courts in Idaho |  |
| TARGET OBJECTIVES |  |
| 1. | Identify gaps in funding, resources, and unmet needs throughout the State |
| 2. | Research how other States are adequately funding Treatment Courts |
| 3. | Develop recommendations and identify strategies to adequately fund treatment courts |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #2 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Identify current funding for treatment courts | Review budgets supporting treatment courts with ISC, district managers, and TCAs | 10/4/2025 | Send listserve or Discord – forms survey – How does the state fund their treatment courts – grant funded, local funding, participant fees – types of funding, participant responsibility, |
| 1. | Uncover funding shortfalls and district disparities | Create surveys for treatment court teams, treatment providers, treatment court coordinators, district managers, and trial court administrators | 11/01/2025 |  |
| 1. | Identify resource gaps | Review the data from surveys. Utilize support from ISC | 12/02/2025 |  |
| 2. | Conduct outreach to different states | Gather and analyze data from 10 different states on how they fund treatment courts | 11/29/2025 |  |
| 3. | Develop funding recommendations and strategies for treatment courts | Create report outlining 5 evidence-based funding strategies | 2/7/2026 |  |

| TEAM LEAD |  |
| --- | --- |
| Aimee Austin | 7th Judicial District Treatment Court |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #2 |  |
| Muffy Davis | Blaine County Commissioner |
| Ashley Bringhurst | 6th Judicial District Treatment Court |
| Jason Dye | 6th Judicial District |
| Ryan Porter | Administrative Office of Courts |
| Darci Dickinson | Administrative Office of Courts |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #2 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #2 |  |

| ACTION ITEM #3 |  |
| --- | --- |
| Explore options for participation in a treatment court without having to move to the location for the treatment court |  |
| FULL DESCRIPTION |  |
| Explore options for participation in a treatment court without having to move to the location for the treatment court. This may include leveraging virtual technology and supervision resources in neighboring jurisdictions. Explore options for funding opportunities for home visits and for transportation |  |
| TARGET OBJECTIVES |  |
| 1. | Explore and consider ways in which individuals may be able to participate in a specialty court with residing within the county. |
| 2. | Consider the pros and cons of out-of-county participation for specialty courts, including obstacles in funding, home visits, whether a program can remain effective with an out of county residence, etc. |
| 3. | Is there a sustainable specialty court model that incorporates the use of virtual technology for some, without compromising the integrity and effectiveness of the specialty court |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #3 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Survey to participants | Competed surveys |  | Sharlene Davis |
| 2. | Survey to providers | Completed surveys |  | Sharlene Davis |
| 3. | Handbook on best practices for telehealth |  |  | Judge Poorman |

| ACTION ITEM #3 TEAM LEAD |  |
| --- | --- |
| Judge Tristan Poorman | 1st Judicial District Magistrate |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #3 |  |
| Judge Faren Eddins | 7th Judicial District Magistrate |
| Sharlene Davis | Administrative Office of Courts |
| Buddy Winters | Veteran’s Treatment Court |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #3 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #3 |  |

| ACTION ITEM #4 |  |
| --- | --- |
| Streamline process of entering treatment court to reach the targeted 50 days from arrest/PV to entrance into treatment court |  |
| FULL DESCRIPTION |  |
| Streamline process of entering treatment court to reach the targeted 50 days from arrest/PV to entrance into treatment court to engage participants more efficiently. Gap analysis needs to be done to determine how long it currently takes vs. the targeted 50 days. |  |
| TARGET OBJECTIVES |  |
| 1. | Perform gap analysis to determine baseline data of courts’ entry processes |
| 2. | Find commonalities with courts that are better able to make the 50-day admission timeline |
| 3. | Work with stakeholders on ways to improve the entry timeline process |
| 4. | Draft process for all courts to utilize to help improve on admitting participants into treatment courts in a more timely fashion |
| 5. | Develop educational materials specifically designed for defense attorneys and potential clients, highlighting the rehabilitative benefits and procedural advantages of treatment courts. By providing comprehensive and easy-to-understand information, the goal is to empower individuals to make informed decisions about their legal and personal well-being. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #4 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET COMPLETION DATE | RESPONSIBLE PARTY |
| 1. | Data Collection | Send out baseline survey to all courts to understand their admission process and timeline | 8/31/2025 | Darci Dickinson |
| 2. | Data Analysis | Analyze baseline survey results and find commonalities among courts that have a lower entry timeframe to see what processes can work in other courts. | 9/30/2025 | Analysis - Look at survey results on common areas |
| 3. | Seek Stakeholder Support | Work with local stakeholders in all counties to generate ideas on how to improve entry timelines in each court/county | 12/31/2025 | Research process of treatment court instead of a PV |
| 4. | Process Change and Implementation | Create processes for all courts to utilize to help all courts lessen the time it takes to be admitted into a treatment court | 2/2/2026 | Should they include a PA or a PD |

| ACTION ITEM #4 TEAM LEAD |  |
| --- | --- |
| Chris Paulson | 3rd Judicial District |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #4 |  |
| Darci Dickinson | Administrative Office of Courts |
| Norm Embry | Latah County Treatment Courts |
| Israel Enriquez | 5th Judicial District Treatment Courts |
| Deputy Patrick Keber | Ada County Sheriff’s Office |
| Kyle Brown | The Center for Hope |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #4 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #4 |  |

| ACTION ITEM #5 |  |
| --- | --- |
| Evaluate the ability to more effectively coordinate through programming and processes the transition from a rider to the community in a treatment court model. |  |
| FULL DESCRIPTION |  |
| Evaluate the ability to more effectively coordinate through programming and processes the transition from a rider to the community in a treatment court model. * This one will be worked on after action item #4 is completed. |  |
| TARGET OBJECTIVES |  |
| 1. |  |
| 2. |  |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #5 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET COMPLETION DATE | RESPONSIBLE PARTY |

| ACTION ITEM #5 TEAM LEAD |  |
| --- | --- |
| Judge Michael Tribe | Court of Appeals |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #5 |  |
| Israel Enriquez | 5th Judicial District Treatment Courts |
| Deputy Keber | Ada County Sheriff’s Office |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #5 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #5 |  |