Crisis Centers – Updated 1/2/2026

Treatment #1: Expand the functionality of crisis centers.

ACTION ITEMS AND OBJECTIVES

- Increase Public Awareness and Understanding of Crisis Center Services

Form a dedicated awareness sub-team to design and implement an outreach campaign that clearly communicates crisis center services and eligibility criteria.

Collaborate with community partners (e.g., law enforcement, hospitals, shelters, schools) to educate front-line personnel on crisis center services and referral processes, ensuring appropriate utilization.

- Expand Crisis Centers for Youth Across Idaho

Facilitate collaborative discussions between Youth Crisis Centers and Youth Assessment Centers to clarify roles, identify potential synergies, and assess feasibility for co-location based on existing program standards.

Conduct a statewide needs assessment to evaluate regional gaps in youth crisis services, ensuring data-driven decisions for new crisis center locations.

- Improve Crisis Center Utilization, Operations, and Coordination

Establish regular statewide meetings for crisis centers and key stakeholders to foster communication, share best practices, and develop strategies to enhance operational efficiency.

Strengthen crisis center networks by promoting resource-sharing and standard operating procedure (SOP) alignment to improve coordination across all centers.

- Ensure Sustainable Statewide Funding and Support for Adult Crisis Centers

Establish a sub-group to define key performance indicators (KPIs), collect testimonials, and compile impact reports that highlight cost-effectiveness and community benefits.

Develop a data collection framework that tracks return on investment (ROI), service utilization, and diversion from higher levels of care, ensuring data consistency across agencies.

Engage leaders and key stakeholders by presenting data-driven reports to secure continued and increased funding for crisis center operations.

| ACTION ITEM #1 |  |
| --- | --- |
| Increase Public Awareness and Understanding of Crisis Center Services |  |
| FULL DESCRIPTION |  |
| TARGET OBJECTIVES |  |
| 1. | Form a dedicated awareness sub-team to design and implement an outreach campaign that clearly communicates crisis center services and eligibility criteria. |
| 2. | Collaborate with community partners (e.g., law enforcement, hospitals, shelters, schools) to educate front-line personnel on crisis center services and referral processes, ensuring appropriate utilization. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #1 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Establish a team responsible for designing and implementing a public outreach campaign that effectively communicates crisis center services. | Sub-team formed by July 2025. | 7/31/2025 | Rebekah Koepnick |
| 1. | Increase public understanding of crisis center services to ensure appropriate utilization and community engagement. | A fully developed and executed outreach campaign. Outreach campaign (strategies) launched by December 2025. | 12/31/2025 | Rebekah Koepnick |
| 2. | Partner with key community organizations to provide training and resources on crisis center services and referral processes. | Identify community partners | 08/31/2025 | Jenna Grant |
| 2. | Ensure front-line personnel have the knowledge and tools to effectively refer individuals to crisis centers. | Conduct 3 awareness sessions by November 2025. | 11/30/2025 | Jenna Grant |
| 2. | Increased awareness and appropriate referrals from community partners. | Measure referral increases by March 2026. | 03/31/2025 | Jenna Grant |

| TEAM LEADS |  |
| --- | --- |
| Rebekah Koepnick | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Jenna Grant | Idaho Department of Health and Welfare, Division of Behavioral Health |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #1 |  |
| Christina Ward | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Dena Baldwin | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Cas Waldron | Southwest District Health |
| Kristien Saldana | Idaho Department of Health and Welfare, Division of Behavioral Health |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #1 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #1 |  |

| ACTION ITEM #2 |  |
| --- | --- |
| Expand Crisis Centers for Youth Across Idaho |  |
| FULL DESCRIPTION |  |
| TARGET OBJECTIVES |  |
| 1. | Facilitate collaborative discussions between Youth Crisis Centers and Youth Assessment Centers to clarify roles, identify potential synergies, and assess feasibility for co-location based on existing program standards. |
| 2. | Conduct a statewide needs assessment to evaluate regional gaps in youth crisis services, ensuring data-driven decisions for new crisis center locations. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #2 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Establish a team to host discussions between Youth Crisis Centers and Youth Assessment Centers to define roles and improve service coordination. | Sub-team developed by June 2025. Stakeholder meetings by August 2025. | 8/31/2025 | Alexis Gygax |
| 1. | Enhance collaboration between youth service providers to optimize service delivery. | Draft collaboration framework by November 2025. | 11/30/2025 | Alexis Gygax |
| 1. | A documented proposal outlining collaboration opportunities. | A documented proposal outlining collaboration opportunities. | 12/31/2025 | Alexis Gygax |
| 2. | Evaluate regional gaps in youth crisis services through data analysis, community feedback, and site visits. | Research phase completed by November 2025. | 11/30/2025 | Yezenia Lora-Salas |
| 2. | A comprehensive needs assessment report with recommendations. | Needs assessment report finalized by January 2026. | 01/31/2026 | Yezenia Lora-Salas |
| 2. | Ensure data-driven decision-making for new crisis center locations. | Implementation planning by March 2026. | 03/31/2026 | Yezenia Lora-Salas |

| TEAM LEAD |  |
| --- | --- |
| Alexis Gygax | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Yezenia Lora-Salas | Idaho Department of Health and Welfare, Division of Behavioral Health |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #2 |  |
| Almedina Toomey | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Sandra Driscoll | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Karen Gonzales | Idaho Department of Health and Welfare, Division of Behavioral Health |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #2 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #2 |  |

| ACTION ITEM #3 |  |
| --- | --- |
| Improve Crisis Center Utilization, Operations, and Coordination |  |
| FULL DESCRIPTION |  |
| TARGET OBJECTIVES |  |
| 1. | Establish regular statewide meetings for crisis centers and key stakeholders to foster communication, share best practices, and develop strategies to enhance operational efficiency. |
| 2. | Strengthen crisis center networks by promoting resource-sharing and standard operating procedure (SOP) alignment to improve coordination across all centers. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #3 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET DATE FOR COMPLETION | RESPONSIBLE PARTY |
| 1. | Directed by a sub-team, implement a structured schedule for statewide meetings to discuss challenges, share best practices, and enhance coordination. | Sub-team formed by June 2025. | 06/30/2025 | Val Seeley |
| 1. | Consistent collaboration through quarterly meetings. | First statewide meeting by September 2025. | 09/30/2025 | Val Seeley |
| 1. | Improve communication and operational efficiency across crisis centers. | Annual report by January 2026. | 01/31/2026 | Val Seeley |
| 2. | Develop a framework for resource-sharing and SOP alignment among crisis centers to enhance service consistency and efficiency. | Needs assessment by November 2025. | 11/30/2025 | Val Seeley |
| 2. | A documented SOP alignment guide and an operational resource-sharing plan. | SOP alignment guide by January 2026. | 10/31/2026 | Val Seeley |
| 2. | Create a more integrated crisis center network with streamlined operations. | Resource-sharing agreements by March 2026. | 03/31/2026 | Val Seeley |

| ACTION ITEM #3 TEAM LEAD |  |
| --- | --- |
| Val Seeley | Idaho Department of Health and Welfare, Division of Behavioral Health |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #3 |  |
| Kristina Trecker | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Alyson Christianson | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Dave Peters | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Dedra Sanna | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Melissa Anstine | Idaho Department of Health and Welfare, Division of Behavioral Health |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #3 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #3 |  |

| ACTION ITEM #4 |  |
| --- | --- |
| Ensure Sustainable Statewide Funding and Support for Adult Crisis Centers |  |
| FULL DESCRIPTION |  |
| TARGET OBJECTIVES |  |
| 1. | Establish a sub-group to define key performance indicators (KPIs), collect testimonials, and compile impact reports that highlight cost-effectiveness and community benefits. |
| 2. | Develop a data collection framework that tracks return on investment (ROI), service utilization, and diversion from higher levels of care, ensuring data consistency across agencies. |
| 3. | Engage leaders and key stakeholders by presenting data-driven reports to secure continued and increased funding for crisis center operations. |

| SMART GOALS TO ACCOMPLISH ACTION ITEM #4 OBJECTIVES |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | SPECIFIC OUTCOME | METRIC FOR ACCOMPLISHMENT | TARGET COMPLETION DATE | RESPONSIBLE PARTY |
| 1. | Form a dedicated group to develop key performance indicators (KPIs), collect and compile data reports. | KPI framework finalized by October 2025. | 10/31/2025 | Alyson Christianson |
| 1. | Provide data-driven evidence to support crisis center funding. | A comprehensive KPI framework and impact report. | 12/31/2025 | Alyson Christianson |
| 2. | Design a standardized system for tracking ROI, service utilization, and diversion from higher levels of care. | Framework design completed by October 2025. | 10/31/2025 | Val Seeley |
| 2. | Establish a reliable and efficient data collection system. | A fully functional, standardized data collection framework. | 07/31/2026 | Val Seeley |
| 3. | Develop and present data-driven reports that showcase crisis center effectiveness and financial benefits. | Funding advocacy report by December 2026. | 10/1/2025 | Alyson Christianson |

| ACTION ITEM #4 TEAM LEAD |  |
| --- | --- |
| Val Seeley | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Alyson Christianson | Idaho Department of Health and Welfare, Division of Behavioral Health |
| OTHER KEY IMPLEMENTATION STAFF FOR ACTION ITEM #4 |  |
| Kristina Trecker | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Dave Peters | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Dedra Sanna | Idaho Department of Health and Welfare, Division of Behavioral Health |
| Melissa Anstine | Idaho Department of Health and Welfare, Division of Behavioral Health |
| CONSULTING STAKEHOLDERS FOR ACTION ITEM #4 |  |
| RESOURCES, RISKS, AND ADDITIONAL INFORMATION FOR ACTION ITEM #4 |  |